## Sheet1
Section | Task | Start Date | End Date
Infra & Security | Deploy EC2 + IAM Roles | 2025-05-15 | 2025-05-21
Infra & Security | Setup X.509 + WAF + IP Allowlist | 2025-05-22 | 2025-05-28
Infra & Security | Logging + Token Rotation | 2025-05-29 | 2025-06-02
VTN Signal Receiver | Build OpenADR 2.0b Listener | 2025-06-03 | 2025-06-06
VTN Signal Receiver | XML Schema Validator + Sanitizer | 2025-06-09 | 2025-06-11
VTN Signal Receiver | Setup Utility Test Harness (VTN Sim) | 2025-06-12 | 2025-06-16
Pseudo-VTN Core | Filter & Translate DR Events | 2025-06-17 | 2025-06-20
Pseudo-VTN Core | Retry Logic + Timeout Handling | 2025-06-23 | 2025-06-25
User & Device Mapping | Utility-User Registration API | 2025-06-26 | 2025-06-30
User & Device Mapping | Opt-In Flow + Device Link | 2025-07-01 | 2025-07-03
User & Device Mapping | Admin UI for Mapping Audit | 2025-07-04 | 2025-07-07
SmartThings Command Bridge | Dispatch DR Signal to Devices | 2025-07-08 | 2025-07-10
SmartThings Command Bridge | Response Validation + Logging | 2025-07-11 | 2025-07-15
SmartThings Command Bridge | Fail Case Handling | 2025-07-16 | 2025-07-18
Audit, Reports, Security | Generate EiReport Payloads | 2025-07-21 | 2025-07-23
Audit, Reports, Security | Encrypted Logs + Storage Hygiene | 2025-07-24 | 2025-07-25
Audit, Reports, Security | Internal Cybersecurity Checklist | 2025-07-28 | 2025-07-29
Admin Monitoring UI | DR Dashboard for Monitoring | 2025-07-30 | 2025-08-04
Admin Monitoring UI | QA Feedback Loop for UI | 2025-08-05 | 2025-08-06
QA + Fail Simulation | Simulate AHRI Test Cases | 2025-08-07 | 2025-08-13
QA + Fail Simulation | Edge Case VTN Testing | 2025-08-14 | 2025-08-18
QA + Fail Simulation | Validate EiReport Format & Timing | 2025-08-19 | 2025-08-20
Deployment | Move to Staging + Load Test | 2025-08-21 | 2025-08-25
Deployment | Move to Acceptance + Field Test | 2025-08-26 | 2025-08-28
Deployment | Move to Production (Limited Rollout) | 2025-08-29 | 2025-09-03
Certification Support | Generate Cert Documentation Pack | 2025-09-04 | 2025-09-09
Certification Support | Lab Coordination (UL, Intertek) | 2025-09-10 | 2025-09-16
Certification Support | Final Review + Compliance Signoff | 2025-09-17 | 2025-09-18